## Sheet1
Timeline
|  |  | Week 4 | week 5 | week 6 | week 7 | week 8 | week 9
|  | Steps | [6 empty] | Planned activity
Feature | Tools required | Subfeature steps | [6 empty] | Work in Progress
| Python | Reimplement the existing code | [6 empty] | Completed | bar: Timeline Week 4
| Python (Pycaret) | Perform Pycaret on Kaggle dataset | bar: Timeline Week 4
Vehicle Health Characteristics | Available dataset, Python coding | Detecting when coolant temperature exceeds the threshold value | bar: Timeline week 5
| Available dataset, Python coding | Detecting when engine oil temperature exceeds the threshold value | bar: Timeline week 5
| Available dataset, Python coding | Detecting when fuel economy drops below the threshold value | bar: Timeline week 5
Road Anamalies | Available dataset (acc. Values ), Python coding | Testing Z- Thresh, Z- diff, etc algortihm and finalizing one | bar: Timeline week 6 to Timeline week 7
Applying the algorithm on available dataset | bar: Timeline week 6 to Timeline week 7
| Python coding image processing (OpenCV library) | Understanding image processing process and code to detect pothole or speed breaker | bar: Timeline week 6 to Timeline week 7
testing on recorded video to check the accuarcy | bar: Timeline week 6 to Timeline week 7
Driving Behavior | Available dataset (engine spped), Python coding | Code to check if acc value of vehicle is greater than threshold value. And to detect driver is ovrespeeding or not. | bar: Timeline week 7 to Timeline week 8
| dataset (engine spped, rpm, throtle position), Python coding (Low code platform) | Pre-processing the data, train the classification model. | bar: Timeline week 7 to Timeline week 8
Finalize the classification model based on accuracy. | bar: Timeline week 7 to Timeline week 8
Implement the classification model on dataset. | bar: Timeline week 7 to Timeline week 8